## Slide 1: Disciplined Agile Delivery: The Foundation for Scaling Agile/Scrum
Scott W. Ambler Senior Consulting Partner
scott [at] scottambler.com
@scottwambler
Disciplined Agile Delivery

## Slide 2: Feel free to ask questions at any time

## Slide 3: Agenda
Disciplined Agile Delivery (DAD)
  A Disciplined Agile Manifesto
  Foundations of DAD
  The DAD Lifecycle
  Goal Driven, Not Prescriptive
  DAD Roles and Teams
Scaling DAD
  What it Means to Scale
  Scaling Agile in Practice
  Agile Practices that Support Scaling
Parting Thoughts

## Slide 4: Part 1 Disciplined Agile Delivery (DAD)

## Slide 5: Exercise: What Are You Doing on Agile Projects?
Organize into teams of 5-8 people
Take a few minutes to introduce yourselves to one another
For 10 minutes, discuss within the team:
  What agile projects have you been on?
  What was different compared with non-agile ones?
  What was the same?
  What types of activities you do to initiate the project and how long did it take? (e.g. Did you do any initial modeling or planning? Did you need to get provide estimates go get funding? Other activities?)
  What activities did you do during construction? (e.g. How did you approach documentation? Planning? Testing?)
  What did you need to do to deploy/release your solution into production? How long did it take?
Someone needs to be a spokesperson for your team
A spokesperson will share a few key learnings with the larger group

## Slide 6: The Agile Manifesto
We value:
Individuals and interactions over processes and tools
Working software over comprehensive documentation
Customer collaboration over contract negotiation
Responding to change over following a plan
That is, while there is value in the items on the right, we value the items on the left more.
  Source: www.agilemanifesto.org
Notes: This manifesto is the work of the organization created as the “Agile Alliance”.
The Agile Manifesto is a set of principles put forth by a group of software development thought leaders that were frustrated with past project failures resulting from overly structured and bureaucratic processes.
The Manifesto was drafted in 2001 by the following individuals:
Kent Beck Mike Beedle Arie van Bennekum Alistair Cockburn Ward Cunningham Martin Fowler James Grenning Jim Highsmith Andrew Hunt Ron Jeffries Jon Kern Brian Marick Robert C. Martin Steve Mellor Ken Schwaber Jeff Sutherland Dave Thomas

## Slide 7: But… DAD Extends Agile Thinking
Solutions, not just software
Stakeholders, not just customers
The organizational ecosystem, not just development teams
Notes: These enhancements reflect the realities faced by most Disciplined Agile Delivery (DAD) teams.
The changes that DAD suggests for the Agile Manifesto are straightforward:
Where the original manifesto focused on software development, a term that too many people have understood to mean only software development, we suggest that it should instead focus on solution delivery.
Where the original manifesto focused on customers, a word that for too many people appears to imply only the business stakeholders, we suggest that it focus on the full range of stakeholders instead.
Where the original manifesto focused on development teams, we suggest that the over- all organizational ecosystem and its improvement be taken into consideration.

## Slide 8: So… A Disciplined Agile Manifesto?
We value:
Individuals and interactions over processes and tools
Working solutions over comprehensive documentation
Stakeholder collaboration over contract negotiation
Responding to change over following a plan
That is, while there is value in the items on the right, we value the items on the left more.
Notes: This manifesto is the work of the organization created as the “Agile Alliance”.
The Agile Manifesto is a set of principles put forth by a group of software development thought leaders that were frustrated with past project failures resulting from overly structured and bureaucratic processes.
The Manifesto was drafted in 2001 by the following individuals:
Kent Beck Mike Beedle Arie van Bennekum Alistair Cockburn Ward Cunningham Martin Fowler James Grenning Jim Highsmith Andrew Hunt Ron Jeffries Jon Kern Brian Marick Robert C. Martin Steve Mellor Ken Schwaber Jeff Sutherland Dave Thomas

## Slide 9: DAD Principles – Extending the Twelve Principles of Agile Software (www.agilealliance.org)
Our highest priority is to satisfy the stakeholder through early and continuous delivery of valuable solutions.
Welcome changing requirements, even late in the solution delivery lifecycle. Agile processes harness change for the customer's competitive advantage.
Deliver working solutions frequently, from a couple of weeks to a couple of months, with a preference to the shorter time scale.
Stakeholders and developers must work together daily throughout the project.
Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done.
The most efficient and effective method of conveying information to and within a delivery team is face-to-face conversation.
Quantified business value is the primary measure of progress.
Agile processes promote sustainable delivery. The sponsors, developers, and users should be able to maintain a constant pace indefinitely.

## Slide 10: DAD Principles – Extending the Twelve Principles of Agile Software (www.agilealliance.org) cont.
Continuous attention to technical excellence and good design enhances agility.
Simplicity – the art of maximizing the amount of work not done – is essential.
The best architectures, requirements, and designs emerge from self-organizing teams.
At regular intervals, the team reflects on how to become more effective, then tunes and adjusts its behavior accordingly.
Leverage and evolve the assets within your organizational ecosystem, and collaborate with the people responsible for those assets to do so.
Visualize workflow to help achieve a smooth flow of delivery while keeping work in progress to a minimum.
The organizational ecosystem must evolve to reflect and enhance the efforts of agile teams, yet be sufficiently flexible to still support non-agile or hybrid teams

## Slide 11: Exercise: Questioning Agile Claims
Get back into your teams
Choose three interesting claims from the following list
  For 10 minutes discuss the three claims as a group
  How true is each claim?
  Is anything being glossed over?
  Reword each claim as “Existing claim although XYZ” – For example, “Development professionals know what to do” becomes “Development professionals know what to do although they aren’t process experts and may not know all options available to them”
Claims:
  Requirements evolve throughout the lifecycle
  Simple designs are best
  Teams should be self-organizing
  Delivery teams don’t need prescriptive process definitions
  Development professionals should validate their own work to the best of their ability
  Disciplined agile teams work in an iterative manner
A spokesperson should be prepared to share a few key learnings with the larger group

## Slide 12: Disciplined Agile Delivery (DAD)
Disciplined Agile Delivery (DAD) is a process decision framework
The key characteristics of DAD:
  People-first
  Goal-driven
  Hybrid agile
  Learning-oriented
  Full delivery lifecycle
  Solution focused
  Risk-value lifecycle
  Enterprise aware
Notes: From this definition, you can see that the DAD process framework has several important characteristics. These characteristics are:
People first
Learning oriented
Agile
Hybrid
IT solution focused
Goal-driven
Delivery focused
Risk and value driven
Enterprise aware

## Slide 13: DAD is a Hybrid Framework
Scrum
Lean
Kanban
Unified Process
Agile Modeling
Agile Data
“Traditional”
Agile Practices
Crystal
…and more
DAD leverages proven strategies from several sources,
providing a decision framework to guide your adoption and
tailoring of them in a context-driven manner.

## Slide 14: The Basic/Agile Lifecycle of Disciplined Agile Delivery (DAD)

## Slide 15: DAD Lifecycle: Advanced/Lean

## Slide 16: The Phases Disappear Over Time
First release:
Inception
Construction
Transition
Second release:
I
Construction
T
Third release:
I
Construction
T
Nth+ releases:
C
C
T
C
C
T
T
T
.
.
.

## Slide 17: DAD Lifecycle: Continuous Delivery

## Slide 18: Exercise: Enterprise Awareness
Get back into your teams
For 10 minutes, discuss:
  What other teams might an agile team need to interact with in your organization?
  Do these teams work in an agile manner? If not, what are you doing to address this?
  What information do your agile teams need to provide to senior management for governance purposes? Why?
  Are your agile teams expected to conform to an existing technical architecture? Organizational business vision? If so, how is this supported?
  Do you have coding guidelines to follow? Data guidelines? Usability? Security? Other? How are they supported or enforced?
  If you were CEO for a day, what would you do to address these issues more effectively?
A spokesperson should be prepared to share a few key learnings with the larger group

## Slide 19: Agile Experiences with Enterprise Awareness
Chart: 
| Ent Tech Arch | Ent Bus Arch | Ent data | Reuse | Port Mgmt | Proc engineering | Governance | Operations | Support | Don't know
Had Failures | 0.32 | 0.28 | 0.26 | 0.04 | 0.23 | 0.23 | 0.47 | 0.45 | 0.21 | 0.23
Had Successes | 0.46 | 0.15 | 0.29 | 0.03 | 0.26 | 0.23 | 0.29 | 0.46 | 0.46 | 0.25
Have your (un)successful agile project teams worked with any of the following teams within the organization? (Please check all that apply)
Source: 2012 Agile Scaling Survey
www.ambysoft.com/surveys/
Notes: Enterprise awareness is an important aspect of self discipline because as a professional you should strive to do what’s right for your organization and not just what’s interesting for you. Teams developing in isolation may choose to build something from scratch, or use different development tools, or create different data sources, when perfectly good ones that have been successfully installed, tested, configured, and fine-tuned already exist within the organization. We can and should do better by doing the following:
Leveraging enterprise assets. There may be many enterprise assets, or at least there should be, which you can use and evolve. These include common development guidelines, such as coding standards, data conventions, security guidelines, and user interface standards. DAD teams strive to work to a common infrastructure; for example, they use the enterprise-approved technologies and data sources whenever possible, and better yet they work to the “to be” vision for your infrastructure. But enterprise assets are far more than standards. If your organization uses a disciplined architecture-centric approach to building enterprise software, there will be a growing library of service-based components to reuse and improve upon for the benefit of all current and future solutions. To do this DAD teams will collaborate with enterprise professionals – including enterprise architects, enterprise business modelers, data administrators, operations staff, and reuse engineers – throughout the lifecycle and particularly during Inception during envisioning efforts. Leveraging enterprise assets increases consistency and thereby ease of maintenance, decreases development costs and time, and decreases operational costs.
Enhancing your organizational ecosystem. The solution being delivered by a DAD team should minimally fit into the existing organizational ecosystem – the business processes and systems supporting them – it should better yet enhance that ecosystem. To do this, the first step is to leverage existing enterprise assets wherever possible as described earlier. DAD teams will work with operations and support staff closely throughout the lifecycle, particularly the closer you get to releasing into production, to ensure that they understand the current state and direction of the organizational ecosystem. DAD teams will often be supported by an additional independent test team which will perform production integration testing (amongst other things) to ensure that your solution works within the target production environment which it will face at deployment time.
Sharing learnings. DAD teams are learning oriented, and one way to learn is to hear about the experiences of others. The implication is that DAD teams must also be prepared to share their own learnings with other teams. Within IBM we support agile discussion forums, informal presentations, training sessions delivered by senior team members, and internal conferences to name a few strategies.
Open and honest monitoring. Although agile approaches are based on trust, smart governance strategies are based on a “trust but verify and then guide” mindset. An important aspect of appropriate governance is the monitoring of project teams through various means. One strategy is for anyone interested in the current status of a DAD project team to attend their daily coordination meeting and listen in, a strategy promoted by the Scrum community. Although it’s a great strategy we highly recommend, it unfortunately doesn’t scale very well because the senior managers responsible for governance are often busy people with many efforts to govern, not just your team. In fact Scott found exactly this in the 2010 How Agile Are You? survey. Another approach, one which we’ve seen to be incredibly effective, is for DAD teams to use instrumented and integrated tooling, such as Rational Team Concert (RTC), which generates metrics in real time that can be displayed on project dashboards. You can see an example of such a dashboard for the Jazz team itself at www.jazz.net, a team following an open commercial strategy. Such dashboards are incredibly useful for team members to know what is going on, let alone senior managers. A third strategy is to follow a risk-driven lifecycle, discussed in the next section, with explicit milestones which provide consistent and coherent feedback as to the project status to interested parties.
See Disciplined Agile Delivery (IBM Press 2012) for a detailed discussion of the importance of enterprise awareness. http://www.ambysoft.com/books/dad.html

## Slide 20: Governance is Built Into DAD
Governance strategies built into DAD:
  Risk-value lifecycle
  Light-weight milestone reviews
  “Standard” opportunities for increased visibility and to steer the team provided by agile
  Enterprise awareness
  Robust stakeholder definition
  Development intelligence via automated dashboards

## Slide 21: Scrum Roles
Scrum
Master
Team
Member
Product
Owner
Notes: Team Lead: Agile process expert, keeps team focused on achievement of goals, removes impediments
Product Owner : Owns the product vision, scope and priorities of the solution
Architecture Owner: Owns the architecture decisions and technical priorities, mitigates key technical risks
Team Member: Cross-functional team members that deliver the solution
Stakeholder: Includes the customer but also other stakeholders such as Project Sponsor, operations, architecture, database groups, governance bodies

## Slide 22: Disciplined Agile Delivery (DAD) Roles
Independent
Tester
Team Lead
Team
Member
Stakeholder
Product
Owner
Architecture
Owner
Specialist
Domain
Expert
Technical
Expert
Integrator
Primary
Roles
Secondary
Roles
(for scaling)
Notes: Team Lead: Agile process expert, keeps team focused on achievement of goals, removes impediments
Product Owner : Owns the product vision, scope and priorities of the solution
Architecture Owner: Owns the architecture decisions and technical priorities, mitigates key technical risks
Team Member: Cross-functional team members that deliver the solution
Stakeholder: Includes the customer but also other stakeholders such as Project Sponsor, operations, architecture, database groups, governance bodies

## Slide 23: Exercise: Transitioning to DAD Roles
Get back into your teams
Choose two of the following “traditional” roles:
  Business analyst
  Project manager
  QA professional
  Database administrator
  Tester
For five minutes, discuss:
  Of the DAD roles previously described, which one(s) are the most likely ones for a person in each role to move to?
  What strengths do they bring to that role?
  What challenges will they face?
A spokesperson should be prepared to share a few key learnings with the larger group

## Slide 24: Forming DAD Teams
Effective teams follow the 4th and 5th principles of the Agile Manifesto:
  Stakeholders and developers must work together daily throughout the project
  Build projects around motivated individuals. Give them the environment and support they need, and trust them to get the job done

## Slide 25: Strategies for Effective Teams
Effective teams:
  Are focused
  Are tailored to the environment
  Are based on trust and respect
  Are safe
  Provide learning opportunities
  Are as small as possible
  Have shared workspaces
  Are “whole”
  Are self-organizing within the constraints of the organization
  Have adequate resources to fulfill their remit
  Are accountable
  Are self-aware
  Are enterprise aware
  Include dedicated people
  Are geographically close
  Follow a common strategy
  Stay together

## Slide 26: Whole Teams
Team members are cross-functional “generalizing specialists”
Better able to collaborate with others and do the work that needs to be done at any point in time
Team works together to deliver the work that they have committed to deliver to the product and architecture owners at the beginning of each iteration

## Slide 27: Exercise: Agile teaming challenges
Get back into your teams
Take 10 minutes to discuss within the team:
  What challenges does your organization face when forming agile teams?
  What experiences have you had with forming small, medium, and large project teams? How did things differ?
  What experiences have you had organizing project teams with different levels of geographic distribution? Everyone in the same work room? Everyone on same floor? Same building? Same city? Same country? Global?
A spokesperson should be prepared to share a few key learnings with the larger group

## Slide 28: Small Teams (2 to 15 People)

## Slide 29: Medium-Sized Teams (10 to 40 people)
Notes: Strategies for medium-sized teams
Increased envisioning and release planning efforts during Inception
Daily subteam and team coordination meetings
Lean daily coordination meetings
Electronic tooling

## Slide 30: Large Teams (30 or More People)
Organizational options:
Feature teams: A subteam works on a feature from end to end.
Component teams: A subteam does all the work for a specific component.
Internal open source: A component is developed via open source techniques.
Notes: Large teams require more coordination in these areas
Project management coordination
Requirements coordination
Technical coordination

## Slide 31: Geographically Distributed/Dispersed Teams

## Slide 32: Potential Challenges When Building Teams
You don’t have adequate agile mentoring
You don’t have team leads that are skilled coaches
You don’t have (enough) generalizing specialists
You don’t have skilled product owners
Your human resources (HR) department is geared toward staffing traditional teams
You don’t have (enough) agile-experienced people
You can’t build a whole team
Not everyone is an agile expert
You don’t know how to identify agile-experienced people
Some of your staff want/need to be directed and not be self-organizing

## Slide 33: DAD is Goal-Driven, Not Prescriptive
Notes: There are various goals that a team needs to address throughout the lifecycle
For each goal there are several issues to consider
For each issue there are different techniques to address it
Each technique has its advantages and disadvantages
Your choices depend on the context of the situation faced by a team

## Slide 34: Goal: Explore the Initial Scope

## Slide 35: Goal: Identify Initial Technical Strategy

## Slide 36: Goal: Address Changing Stakeholder Needs

## Slide 37: Goal: Produce a Potentially Consumable Solution

## Slide 38: Exercise: Tailoring Factors
Get back into your smaller teams
Take 10 minutes to discuss within the team:
  Considering the goal diagrams on the previous slide, what factors would you decide how to tailor your approach?
  Where possible, discuss actual agile projects and compare the differences in situations that you faced
A spokesperson will share a few key learnings with the larger group

## Slide 39: Part 2 Scaling DAD

## Slide 40: Scaling/Tailoring Complexity Factors
motivates
motivates
motivates
motivates
affects
varies by
varies by
motivates
affects
affects
Geographic
Distribution
Co-located
Global
Organizational
Distribution
Single
Outsourcing
Team
Size
2
1000s
Domain Complexity
Straightforward
Very complex
Technical Complexity
Straightforward
Very complex
Compliance
None
Life critical
Team
Culture
Agile
Rigid
Organizational
Culture
Agile
Rigid
Notes: How a team chooses to tailor DAD to address the goals will depend on several factors:
  Geographical distribution
  Team size
  Regulatory compliance (internal and external)
  Domain complexity
  Technical complexity
  Organizational distribution
  Team culture
  Organizational culture

## Slide 41: Exercise: Exploring the Initial Scope
Get back into your smaller teams
  Goal:
    In 10 min create a project profile focused on exploring the initial scope
Instructions:
  Identify the team member(s) who have been involved with an agile team where some initial requirements elicitation occurred. If there are several, quickly discuss each project and choose the one most interesting to you
  Describe how the team approached initial requirements elicitation – How much effort was it? What artifacts were created? Who was involved? How was the output used by the team? How were the requirements validated?
  Describe the project, considering the complexity factors described previously
  What are the advantages and disadvantages of what the team did? Think short term and long term.
A spokesperson will share a few key learnings with the larger group

## Slide 42: Agile Experiences with Team Size
On your (un)successful agile projects, how many IT team members were there?
Source: 2012 Agile Scaling Survey
www.ambysoft.com/surveys/
Notes: Original source data, questions, and a slide deck are available free of charge at www.ambysoft.com/surveys/

## Slide 43: Large Teams
Organizational options:
Feature teams: A subteam works on a feature from end to end.
Component teams: A subteam does all the work for a specific component.
Internal open source: A component is developed via open source techniques.
Notes: Large teams require more coordination in these areas
Project management coordination
Requirements coordination
Technical coordination

## Slide 44: Exercise: Large Team Organization
Get back into your smaller teams
Instructions:
  Take 10 minutes to discuss the feature team, component team, and internal open source organizational strategies
  What are the advantages and disadvantages of each?
  What do you need to do to make each strategy work? During Inception, Construction, and Transition?
  How would each strategy affect the goals of Identify an Initial Technical Strategy and Produce a Potentially Consumable Solution
A spokesperson will share a few key learnings with the larger group

## Slide 45: Agile Experiences with Geographic Distribution
On your (un)successful agile projects, how distributed were team members?
Source: 2012 Agile Scaling Survey
www.ambysoft.com/surveys/
Notes: Original source data, questions, and a slide deck are available free of charge at www.ambysoft.com/surveys/

## Slide 46: Geographically Distributed/Dispersed Teams

## Slide 47: Exercise: Geographically Distributed Teams
Get back into your smaller teams
Instructions:
  Take 10 minutes to discuss the implications of the team distribution strategies
  What are the advantages and disadvantages of each?
  What do you need to do to make each strategy work? During Inception, Construction, and Transition?
  How would each strategy affect the goals of Identify an Initial Technical Strategy and Produce a Potentially Consumable Solution
A spokesperson will share a few key learnings with the larger group

## Slide 48: Agile Experiences with Compliance
On your (un)successful agile projects, was compliance applicable?
Note: Self imposed = CMMI, ISO, …
Source: 2012 Agile Scaling Survey
www.ambysoft.com/surveys/
Notes: Original source data, questions, and a slide deck are available free of charge at www.ambysoft.com/surveys/

## Slide 49: Agile Experiences with Domain Complexity
Chart: 
| High Risk | Complex | Medium complexity | Straightforward | Pilot Projects
Had Failures | 0.19 | 0.51 | 0.51 | 0.28 | 0.21
Had Successes | 0.26 | 0.43 | 0.68 | 0.54 | 0.47
Question: From the point of view of the problem/business domain, at what level(s) of complexity has the organization (un)successfully applied agile techniques? (Please check all that apply)
Source: 2012 Agile Scaling Survey
www.ambysoft.com/surveys/

## Slide 50: Agile Experiences with Technical Complexity
Chart: 
| Multi-platform | Single platform | Fix legacy data | Access legacy data | Fix legacy systems | System integration | Package/COTS | Stand-alone | Greenfield
Had Failures | 0.36 | 0.21 | 0.17 | 0.3 | 0.4 | 0.55 | 0.28 | 0.23 | 0.45
Had Successes | 0.42 | 0.62 | 0.28 | 0.48 | 0.46 | 0.68 | 0.26 | 0.54 | 0.66
Question: In which technical situations has the organization (un)successfully applied agile approaches? (Please check all that apply)
Source: 2012 Agile Scaling Survey
www.ambysoft.com/surveys/

## Slide 51: Agile Experiences with Organizational Distribution
Chart: 
| Outsourcing | Partner organizations | Contractors/consultants | Several countries | Several divisions | Same division
Had Failures | 0.17 | 0.28 | 0.55 | 0.38 | 0.51 | 0.34
Had Successes | 0.2 | 0.31 | 0.59 | 0.4 | 0.63 | 0.71
Question: In which of the following situations has the organization (un)successfully applied agile techniques? (Please check all that apply)
Source: 2012 Agile Scaling Survey
www.ambysoft.com/surveys/

## Slide 52: “Common” Agile Practices that Support Scaling
Continuous Coordination
  Coordination meetings – e.g. “Daily stand ups”
  Development intelligence
  Demos
Short iterations/sprints
Regularly producing a potentially consumable solution – e.g. Potentially shippable software in Scrum
Continuous integration
  Better yet continuous deployment
Agile planning
  Initial high-level release planning
  Just in time (JIT) detailed planning – e.g. Iteration/sprint planning
  Look-ahead planning

## Slide 53: Some “Additional” Practices for Scaling Agile
Agile Modeling (and Documentation)
API First
Continuous Deployment
Parallel Independent Testing
Leadership Teams
Multiple Backlog Management

## Slide 54: Agile Modeling’s Best Practices
Notes: www.agilemodeling.com/essays/bestPractices.htm
This is a “practices map”, showing several practices and relationships between them.

## Slide 55: Some Industry Stats
2009 Agile Project Initiation Survey:
  89% of agile teams do some sort of up-front requirements modeling
  86% of agile teams do some sort of up-front architecture modeling
  56% create a project vision/chart document
2008 Test-Driven Development Survey
  When it came to requirements capture, 85% of respondents wrote some documentation, 53% did some modeling, and 45% wrote acceptance tests
  When it came to design capture, 80% wrote documentation, 67% modeled, and 57% wrote developer tests
Survey details can be obtained free of charge at Ambysoft.com/surveys/

## Slide 56: API First
When there are many people developing a shared set of components you should invest time at the beginning of the project to identify the components and define the interfaces to those components
  “Component” is used to indicate any shared technical resource such as a set of web services, a shared data source, a programming library, a framework, and so on
  Many teams will choose to write the interface stubs and tests at this time so that they have something to integrate
Effectively a rigorous application of Agile Model’s Architecture Envisioning and Just Barely Good Enough practices
API First is a practice of The Eclipse Way
Also known as Contract Model in Agile Modeling

## Slide 57: Continuous Deployment (CD)

## Slide 58: Parallel Independent Testing

## Slide 59: Leadership Teams
For large teams there are several coordination subteams:
  Architecture Owners – Responsible for technical coordination
  Product Owners – Responsible for requirements coordination
  Project Management – Responsible for team coordination and management
How it works:
  Early in the project the respective visions are agreed to by key members of each coordination team (plus others)
  Throughout the project these teams coordinate their respective issues on a regular basis with one another

## Slide 60: Multiple Backlogs
There are dependencies between work items (including requirements)
When large teams are separated into subteams, and if each subteam has its own work items, then these dependencies need to be managed
Product Owners are responsible for the work items, therefore they need to coordinate dependencies with one another

## Slide 61: Exercise: Process Tailoring #1
Get back into your smaller teams
Goal: Develop a process strategy for a new project team
Instructions:
  Take 10 minutes to identify how you would approach Inception, Construction, and Transition for the given project scenario
Scenario:
  Your organization is new to agile but has recently hired 3 disciplined agile coaches and invested in some disciplined agile training
  People within your organization are fairly specialized in traditional roles such as business analysis, programmer, tester, and so on
  Your business stakeholders insist on being presented with a description of what you will develop, a +/- 10% cost estimate, and a month-based delivery date (e.g. June 2013) before they will fund development
  Your first project will have eight developers co-located in a single room
  Your stakeholders are in different buildings in the same city as your developers
  Your operations team only has experience with traditional release processes
A spokesperson will describe your approach with the larger group

## Slide 62: Exercise: Process Tailoring #2
Get back into your smaller teams
Goal: Develop a process strategy for a new project team
Instructions: Take 10 minutes to work through the given project scenario
Scenario:
  Your organization has recently merged with an equal sized competitor in another country. Each organization has an IT group with about 20 developers. There are an additional 5 people who work from home around the globe.
  Both organizations are very experienced with small team, co-located agile development
  Your organization has also recently contracted with an Indian outsourcing firm to take over system integration, security, and performance testing
  International legislation requires IT development teams to document their work and provide full traceability throughout the lifecycle
  Your project will be to integrate the systems of your two organizations. There is some overlap between systems, each organization has some unique systems, and there are significant differences in source data. The systems range in age from 2 years to 30 years old, running on different platforms. Some systems have full regression test suites, some have partial suites, and some have manual test cases.
  This project is the largest one your organization has ever taken on, with an estimated 30 people required for the team
A spokesperson will share a few key learnings with the larger group

## Slide 64: Disciplined Agile Delivery: The Foundation for Scaling Agile
Disciplined Agile Delivery (DAD)
Scrum
Lean
Kanban
Unified Process
Agile Modeling
And more…
“Traditional”
Agile Practices
Team Size
Geographic
Distribution
Compliance
Domain Complexity
Technical
Complexity
Organizational
Distribution
Team Culture
Organizational
Culture
DAD leverages proven strategies from several sources,
providing a decision framework to guide your adoption and
tailoring of them in a context-driven manner.

## Slide 65: Agile Experiences with Organizational Complexity
Chart: 
| Waterfall culture | Lack of trust | Lack of stakeholder involvement | Waterfall governance | Specialized IT staff | Command and control culture | Differing visions | Management resistance | Stakeholder resistance | Needed coaching
Had Failures | 0.68 | 0.66 | 0.62 | 0.49 | 0.3 | 0.6 | 0.38 | 0.3 | 0.32 | 0.38
Had Successes | 0.75 | 0.63 | 0.71 | 0.41 | 0.39 | 0.54 | 0.37 | 0.22 | 0.26 | 0.35
Question: What challenges have (un)successful teams have experienced while adopting agile approaches? (Please check all that apply)
Source: 2012 Agile Scaling Survey
www.ambysoft.com/surveys/

## Slide 66: Exercise: What Have You Learned?
Individually, on a sheet of paper, answer the following questions:
  What three new things have you learned about agile delivery in general?
  What three new things have you learned about scaling agile approaches?
  What improvements in the way you approach agile project will you try to adopt when you’re back at work?
  What still puzzles you?

## Slide 67: A Disciplined Ending….
Please…
  Take the opportunity to thank your teammates – we all learned together
  Fill out the workshop evaluation form(s)
  Turn in the evaluation(s) to the instructor

## Slide 68: Thank You!
scott [at] scottambler.com
@scottwambler
Disciplined Agile Delivery
AgileModeling.com
AgileData.org
Ambysoft.com
DisciplinedAgileDelivery.com
EnterpriseUnifiedProcess.com
ScottAmbler.com

## Slide 69: Recommended Resources